## Sheet1
WBS |  | Dates |  | POCs |  |  |  |  | Status
# | Name | Start | Finish | Chewning, Kurt | Greene, Jennifer | Manley, Dave | Smith, Jeanette | Smith, John
1. | Project Management | 2009-08-31 | 2009-12-18 |  |  |  | Lead |  | On-Going
1.1 | Organize Team | 2009-08-31 | 2009-08-31 | All | All | All | All | All | Complete
1.2 | Select Concept | 2009-09-01 | 2009-09-04 | All | All | All | All | All | Complete
1.3 | Generate Project Proposal | 2009-09-05 | 2009-09-14 |  |  |  | Lead |  | Complete
1.3.1 | Project Proposal Presentation | 2009-09-04 | 2009-09-13 | SME |  |  |  |  | Complete
1.3.2 | Project Proposal Summary | 2009-09-04 | 2009-09-13 |  |  |  |  | SME | Complete
1.3.3 | Proposal Scoped and Approved | 2009-09-14 | 2009-09-14 | All | All | All | All | All | Complete
1.4 | Project Management Plan | 2009-09-05 | 2009-09-12 |  |  | SME |  |  | Complete
1.5 | Networked Schedule | 2009-09-13 | 2009-09-20 |  |  | SME |  |  | Complete
1.6 | System Buisiness Concept | 2009-09-15 | 2009-09-23 |  |  | SME |  |  | On-Going
1.7 | SOW | 2009-09-15 | 2009-09-23 |  |  |  | SME |  | Complete
1.8 | Reporting | 2009-10-17 | 2009-12-18 |  |  |  | Lead
1.8.1 | Final Presentation | 2009-10-17 | 2009-12-18 | SME
1.8.1.1 | Rough Draft Presentation | 2009-10-17 | 2009-11-13 | SME
1.8.1.2 | Final Draft Presentation | 2009-11-14 | 2009-12-18 | SME
1.8.2 | Final Report | 2009-10-17 | 2009-12-18 |  | SME
1.8.2.1 | Rough Draft Report | 2009-10-17 | 2009-11-13 |  | SME
1.8.2.2 | Final Draft Report | 2009-11-14 | 2009-12-18 |  | SME
2.0 | Systems Engineering Management | 2009-09-15 | 2009-12-18 |  | Lead
2.1 | Systems Engineering Tools Selection | 2009-09-15 | 2009-09-15 | All | All | All | All | All | Complete
2.2 | CM | 2009-09-15 | 2009-12-18 |  | SME |  |  |  | On-Going
2.3 | Systems Engineering Management Plan (SEMP) | 2009-09-15 | 2009-10-05 |  | SME |  |  |  | On-Going
2.4 | Risk Management Plan (RMP) | 2009-09-15 | 2009-10-05 |  | SME |  |  |  | On-Going
2.5 | Product Assurance Plan (PAP) | 2009-09-15 | 2009-10-05 |  | SME |  |  |  | On-Going
3.0 | System Design | 2009-09-15 | 2009-10-16 | All | All | All | All | All | On-Going
3.1 | Define System Level Problem | 2009-09-15 | 2009-09-26 |  |  |  |  | Lead | Complete
3.1.1 | Develop Concept of Operations | 2009-09-15 | 2009-09-16 |  | SME |  |  |  | Complete
3.1.2 | Develop Use Cases | 2009-09-15 | 2009-09-23 |  |  | SME |  |  | Complete
3.1.3 | Develop External Systems Activity Diagram | 2009-09-15 | 2009-09-23 |  |  | SME |  |  | Complete
3.1.4 | Develop External Systems Diagram | 2009-09-15 | 2009-09-16 |  |  |  |  | SME | On-Going
3.1.5 | Develop Systems Objectives Hierarchy | 2009-09-15 | 2009-09-16 |  |  | SME |  |  | Complete
3.1.6 | Develop Analyze and Refine Requirements | 2009-09-17 | 2009-09-25 |  |  |  | SME | SME | On-Going
3.1.7 | Obtain Approval for Requirements | 2009-09-25 | 2009-09-25 | All | All | All | All | All
3.1.8 | Document Final Requirements | 2009-09-26 | 2009-09-26 |  |  |  |  | SME
3.2 | Develop System Functional Architecture | 2009-09-27 | 2009-10-03 |  |  | Lead
3.2.1 | Create Simple Functional Concept | 2009-09-27 | 2009-09-27 |  |  | SME |  |  | Complete
3.2.2 | Draft and Evaluate Functional Model | 2009-09-28 | 2009-09-30 |  |  | SME |  |  | On-Going
3.2.2.1 | Conduct Functional decomposition Brainstorming | 2009-09-28 | 2009-09-28 | All | All | All | All | All | Complete
3.2.2.2 | Conduct Fiunctional Decomposition Trade Study | 2009-09-29 | 2009-09-29 |  |  | SME |  |  | Complete
3.2.2.3 | Select Functional Decomposition | 2009-09-30 | 2009-09-30 | All | All | All | All | All | Complete
3.2.3 | Complete Functional and Data Models | 2009-10-01 | 2009-10-01 |  | SME |  |  |  | On-Going
3.2.3.1 | Generate Initial Functional Models | 2009-10-01 | 2009-10-01 |  | SME |  |  |  | Complete
3.2.3.2 | Generate System Activity Diagrams | 2009-10-01 | 2009-10-01 |  |  | SME
3.2.3.3 | Identify / Draft Sub-System Interface Requirements | 2009-10-01 | 2009-10-01 |  | SME | SME |  |  | On-Going
3.2.4 | Trace Input / Output Requirements | 2009-10-02 | 2009-10-02 |  | SME |  |  |  | On-Going
3.2.4.1 | Complete Draft IDEF A0 Diagram | 2009-10-02 | 2009-10-02 |  | SME |  |  |  | On-Going
3.2.4.2 | Complete Draft IDEF A1 Diagram | 2009-10-02 | 2009-10-02 |  |  | SME | SME | SME
3.2.5 | Obtain Approval for Functional Architecture | 2009-10-03 | 2009-10-03 | All | All | All | All | All
3.2.6 | Document Final Functional Architecture | 2009-10-03 | 2009-10-03 |  | SME | SME | SME | SME
3.3 | Develop System Instantiated Architecture | 2009-10-04 | 2009-10-16 | Lead
3.3.1 | Develop Generic Architecture | 2009-10-04 | 2009-10-06 | All | All | All | All | All
3.3.1.1 | Brainstorm Architecture | 2009-10-04 | 2009-10-04 | All | All | All | All | All
3.3.1.2 | Generate Trade-Offs | 2009-10-05 | 2009-10-05 | SME | SME | SME | SME | SME
3.3.1.3 | Down-Select Generic Architecture | 2009-10-06 | 2009-10-06 | All | All | All | All | All
3.3.2 | Develop Instantiated Achitecture | 2009-10-07 | 2009-10-15 | All | All | All | All | All
3.3.2.1 | Brainstorm Instantiated Architecture Components | 2009-10-07 | 2009-10-07 | All | All | All | All | All
3.3.2.2 | Generate Morphological Box - Instantiated Sys Arch Sub-Sys | 2009-10-08 | 2009-10-09 | SME | SME | SME | SME | SME
3.3.2.3 | Conduct Sub-System Trade-Off Analysis | 2009-10-10 | 2009-10-12 | SME | SME | SME | SME | SME
3.3.2.4 | Down Select Instantiated Architecture | 2009-10-13 | 2009-10-13 | All | All | All | All | All
3.3.2.5 | Finalize Sub-System Interface Requirenents | 2009-10-14 | 2009-10-14 | SME | SME | SME | SME | SME
3.3.2.6 | Document Instantiated Draft Design | 2009-10-15 | 2009-10-15 | SME | SME | SME | SME | SME
3.3.3 | Obtain Approval for Instantiated Architecture | 2009-10-15 | 2009-10-15 | All | All | All | All | All
3.3.4 | Final Instantiated Design | 2009-10-16 | 2009-10-16 | All | All | All | All | All
4.0 | Refine / Update Design | 2009-10-17 | 2009-12-15 | All | All | All | All | All
4.1 | System Requirements | 2009-10-17 | 2009-12-15 |  |  |  |  | Lead
4.2 | Functional Design | 2009-10-17 | 2009-12-15 |  |  | Lead
4.3 | Instantiated Design | 2009-10-17 | 2009-12-15 | Lead
| Legend: | All | All team memebers participate in this task
|  | Lead | Responsible for leading a major project effort
|  | SME | Responsible for conducting a specific task
|  | Complete | Task is complete
|  | On-Going | Started work on task, but iut is not complete
Task not started